## 12A DEV 5005
FORM 12A: CUMULATIVE QUARTERLY MTEF TARGET MONITORING FORM MEF 7.1
VOTE: 803047 VOTE NAME: MTWARA DISTRICT COUNCIL
PERIOD COVERED: QUARTER ENDING JUNE 30, 2017 IN FINANCIAL YEAR: 2016/2017
BUDGET COVERAGE: DEVELOPMENT
PROJECT CODE AND NAME: 4902 - DISTRICT DEVELOPMENT PROJECT
SUB-VOTE CODE AND NAME: 5005 -PLANNING,TRADE AND ECONOMY
OBJECTIVE CODE AND NAME: C- IMPROVE ACCESS,QUALITY AND EQUITABLE SOCIAL SERVICES DELIVERY.
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
CO3D |  |  | √ | Council headquarter and Investment building constructed by June,2019 | Payment of contractors debts for construction of maternal ward, staff house at Nanguruwe Health Centre and supplying solar refrigirators to the Dispensaries done. | 49.05 | √ |  |  | 163107155 | 83107155 | 50.9525 | Payment to contractors done
CO7D |  |  | √ | Council District participatory development plan and budget prepared by June, 2019 | M&E carried out | 17.2 | √ |  |  | 54000000 | 9289648.4 | 17.2031 | Work onprogress
PROJECT CODE TOTAL | [9 empty] | 217107155 | 101686451.8 | 68.1555
PROJECT CODE AND NAME: 6277- LOCAL GOVT SUPPORT PROGRAMME
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
C01C |  |  | √ | PPP model of financing used atleast 4 projects write-ups by June 2019 | Not carried out | 0 | √ |  |  | 23900000 | 0 | 0 | Fund not released
C02D |  |  | √ | Council District Participatory development plan and budget prepared by June, 2019 | Not carried out | 0 | √ |  |  | 79000000 | 0 | 0 | Fund not released
C05S |  |  | √ | Annual District participatory development plan and budget prepared by June, 2019 | Payment of conference facilities,diesel,per-diem and office consumable | 67 | √ |  |  | 24700000 | 20553370.4 | 83.212 | On progress
C06D |  |  | √ | Council headquarter and Investment building constracted by June, 2019 | Not carried out | 0 | √ |  |  | 25000000 | 0 | 0 | Fund not released
C01S |  |  | √ | PPP model of financing used atleast 4 projects write-ups by June 2019 | Not carried out | 0 | √ |  |  | 39226600 | 0 | 0 | Fund not released
PROJECT CODE TOTAL | [9 empty] | 191826600 | 20553370.4
PROJECT CODE AND NAME: 6460- HALMASHAURI YA WILAYA/MANISPAA JIJI
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYP | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
C04D |  |  | √ | Council District participatory Development plan and budget prepared by June, 2019. | Projects frm the villages aproved by the council constituent committee | 100 | √ |  |  | 29337000 | 36590000 | 124.723 | 1200 bags of cement supplied to Dihimba, Manamawa, Namkapi, Njumbuli, Lyowa and Mdui villages
PROJECT CODE TOTAL | [9 empty] | 29337000 | 36590000 | 124.723
SUB-VOTE TOTAL | [9 empty] | 438270755 | 158829822.2
PROJECT CODE AND NAME: 4902 - DISTRICT DEVELOPMENT PROJECT
SUB-VOTE CODE AND NAME: 5007 - PRIMARY EDUCATION
OBJECTIVE CODE AND NAME: C- IMPROVE ACCESS,QUALITY AND EQUITABLE SOCIAL SERVICES DELIVERY.
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
C07D |  |  | √ | Increase number of teachers houses from 861 to 871 by June, 2019 | Not perfomed | 0 | √ |  |  | 50000000 | 0 | 0 | Fund not received
C08D |  |  | √ | Reduce class ratio of pupils from 1:69 to 1:40 for primary schools and 1:320 of pre - primary to 1:150 by June 2019 | Fund transfer to Mkungu village account for construction of classroom | 6.25 | √ |  |  | 80000000 | 5000000 | 6.25 | work on progress
C09D |  |  | √ | Pupils desk ratio reduced from 1:3 to 1:2 by June, 2019 | pupils desk prodused | 75 | √ |  |  | 50000000 | 32335500 | 64.671 | work on progress
C10D |  |  | √ | Reduce pupils ratio in pit latrine holes for girls from 1:49 to 1:20 and boys from1:55 to 1:25 by June, 2019 | Not perfomed | 0 | √ |  |  | 40000000 | 0 | 0 | Fund not received
PROJECT CODE TOTAL | [9 empty] | 220000000 | 37335500
PROJECT CODE AND NAME: 6277-LOCAL GOVT SUPPORT PROGRAMME
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
C11D |  |  | √ | Reduce class ratio pupils from 1:69 to 1:40 for primary schools and 1:320 of pre-primary to 150 by June 2019 | Constraction of classrooms at Ilala, Nanyati and Mnomo Primary schools and pit latrine at Mgao, Utende, Mnete ,Naumbu, Imekuwa, and Namgogoli Primary schools | 97.8 | √ |  |  | 50000000 | 48900000 | 97.8 | Work onprogress
PROJECT CODE TOTAL | [9 empty] | 50000000 | 48900000 | 97.8
SUB-VOTE TOTAL | [9 empty] | 270000000 | 86235500
PROJECT CODE AND NAME:4902 - DISTRICT DEVELOPMENT PROJECT
SUB-VOTE CODE AND NAME: 5008 -SECONDARY EDUCATION
OBJECTIVE CODE AND NAME: D - INCREASE QUANTITY AND QUALITY OF SOCIAL SERVICES AND INFRASTRUCTURE.
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
C02D |  |  |  | Advanced Secondary Schools constructed in 4 wards by June, 2019 | Not perfomed |  | √ |  |  | 177000000 | 0 | 0
C03D |  |  | √ | Students desk ratio reduced from 1:2 to 1:1 by June, 2019 | Student's desks manufactured | 50 | √ |  |  | 18000000 | 9494996 | 52.75 | Desks produced
PROJECT CODE TOTAL | [9 empty] | 195000000 | 9494996 | 52.75
PROJECT CODE AND NAME: 6277- LOCAL GOVT SUPPORT PROGRAMME
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
CO4D |  |  | √ | Construction of 10 Secondary Schools Laboratories by June 2019. | 1000 roof sheets, 1200 bags of cement, flat bars and squire pipes for laboratories construction purchased and construction of classroom at Libobe and Madimba Secondary schools and rehabilitation of Nanguruwe Secondary schools | 102.38 | √ |  |  | 110000000 | 152547089.36 | 138.6792 | On progress
PROJECT CODE TOTAL | [9 empty] | 110000000 | 152547089.36 | 138.6792
SUB-VOTE TOTAL | [9 empty] | 305000000 | 162042085.36
PROJECT CODE AND NAME: 4902 - DISTRICT DEVELOPMENT PROJECT
SUB-VOTE CODE AND NAME: 5009 - LAND DEVELOPMENT & URBAN PLANNING
OBJECTIVE CODE AND NAME: D - INCREASE QUANTITY AND QUALITY OF SOCIAL SERVICES AND INFRASTRUCTURE.
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
CO1D |  |  | √ | 1000 plots of Land for investment, Industrial, commercial and residual are planned and surveyed by June, 2019 | Valuation of Council properties carried out | 30.75 | √ |  |  | 54150000 | 16650000 | 30.7479 | Valuation on District's properties conducted
C03C |  |  | √ | 10 Villages Land use plan are prepared by June, 2019 | Not perfomed | 0 | √ |  |  | 10662845 | 0 | 0 | Fund not received
C01C |  |  |  | 1000 plots of Land for investment, Industrial, commercial and residual are planned and surveyed by June, 2019 | Submission of drawings to the Ministry of Land for approval | 12.95 | √ |  |  | 7350000 | 952000 | 12.9524 | Work onprogress
PROJECT CODE TOTAL | [9 empty] | 72162845 | 17602000 | 24.3921
SUB-VOTE TOTAL | [9 empty] | 72162845 | 17602000
PROJECT CODE AND NAME: 4902 - DISTRICT DEVELOPMENT PROJECT
SUB-VOTE CODE AND NAME: 5036 -ENVIRONMENTS
OBJECTIVE CODE AND NAME: H - MANAGEMENT OF NATURAL RESOURCES AND ENVIRONMENT IMPROVED.
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
HO2D |  |  | √ | Environmental and Natural resources conservations established by June, 2019 | Awareness to the community created on environmental conservation | 7 | √ |  |  | 14300000 | 1080000 | 7.5524 | Work on progress
PROJECT CODE TOTAL | [9 empty] | 14300000 | 1080000 | 7.5524
SUB-VOTE TOTAL | [9 empty] | 14300000 | 1080012
PROJECT CODE AND NAME: 4902 - DISTRICT DEVELOPMENT PROJECT
SUB-VOTE CODE AND NAME: 5012 -HEALTH CENTRES
OBJECTIVE CODE AND NAME: C - IMPROVE ACCESS,QUALITY AND EQUITABLE SOCIAL SERVICES DELIVERY
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
C10D |  |  | √ | Shortage of health facilities infrastructures reduced from 62% to 40% by June 2019 | Not perfomed | 0 | √ |  |  | 110000000 | 0 | 0 | Fund not received
PROJECT CODE TOTAL | [9 empty] | 110000000 | 0 | 0
PROJECT CODE AND NAME: 6277 - LOCAL GOVT SUPPORT PROGRAMME
SUB-VOTE CODE AND NAME: 5010 -HEALTH SERVICES
OBJECTIVE CODE AND NAME: C - IMPROVE ACCESS,QUALITY AND EQUITABLE SOCIAL SERVICES DELIVERY
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
C11D |  |  | √ | Shortage of health facilities infrastructures reduced from 62% to 40% by June 2019 | Fund transfered to Mbuo, Makome A, Makome B, Mtama, and Nanyani village account for construction of staff houses | 37.5 | √ |  |  | 80000000 | 30000000 | 37.5 | Work on progress
PROJECT CODE TOTAL | [9 empty] | 80000000 | 30000000 | 37.5
SUB-VOTE TOTAL | [9 empty] | 190000000 | 30000000 | 37.5
PROJECT CODE AND NAME: 5405 - UNICEF support to Health.
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
C12C |  |  | √ | To raise household uptake of adquately iodated salt from 13.3% to 27% in Mtwara DC by June, 2019 | Monitoring and supervision of salt farms on iodated salt carried out four quartererly inspection to 28 salt farms and joint quarterly stakeholder coordination meeting | 82.95 | √ |  |  | 43000000 | 35666750 | 82.9459 | Work on progress
PROJECT CODE TOTAL | [9 empty] | 43000000 | 35666750 | 82.9459
SUB-VOTE TOTAL | [9 empty] | 43000000 | 35666750
PROJECT CODE AND NAME: 4902 - DISTRICT DEVELOPMENT PROJECT
SUB-VOTE CODE AND NAME: 5017 - RURAL WATER SUPPLY.
OBJECTIVE CODE AND NAME: C- IMPROVE ACCESS,QUALITY AND EQUITABLE SOCIAL SERVICES DELIVERY.
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
C10D |  |  | √ | Coverage to improved access to water supply services for rural proportion of people increased from 45% to 85% by June, 2019 | Maintenance of Mbuo and Nanguruwe water projects performed.construction of new project Namanjele water supply | 10.93 | √ |  |  | 50000000 | 25466000 | 50.932 | Fund deposited to the COWSO accounts of Mbuo and Nanguruwe.
PROJECT CODE TOTAL | [9 empty] | 50000000 | 25466000 | 50.932
PROJECT CODE AND NAME: 6277-LOCAL GOVT SUPPORT PROGRAMME
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent | REMARKS ON IMPLEMENTATION
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
C08D |  |  | √ | Coverage to improved access to water supply services for rural proportion of people increased from 45% to 85% by June, 2019 | Not conducted | 0 | √ |  |  | 30000000 | 0 | 0 | Fund not received
PROJECT CODE TOTAL | [9 empty] | 30000000 | 0 | 0
PROJECT CODE AND NAME: 3280-RURAL WATER SUPPLY & SANITATION
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
C07D |  |  | √ | Coverage to improved access to water supply services for rural proportion of people increased from 45% to 85% by June, 2019 | Complition of development project in progress | 68 | √ |  |  | 165650000 | 4338570398.91 |  | Work on progress
PROJECT CODE TOTAL | [9 empty] | 165650000 | 4338570398.91 | 0
SUB-VOTE TOTAL | [9 empty] | 245650000 | 4364036398.91 | 50.932
PROJECT CODE AND NAME: 6393 - support to TASAF
SUB-VOTE CODE AND NAME: 5027 - COMM DEVT, GENDER & CHILDREN
OBJECTIVE CODE AND NAME: D - INCREASE QUANTITY AND QUALITY OF SOCIAL SERVICES AND INFRASTRUCTURE
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
D10C |  |  | √ | Vulnerable groups in 99 Villages enhenced by June, 2019 | From July- June total of 10,155 vulnerable households in 99 villages facilitated, | 91.1 | √ |  |  | 2246454000 | 2046592520 | 91.1032 | Work implemented
[10 empty] | 2246454000 |  | 91.1032
SUB-VOTE TOTAL | [9 empty] | 2246454000
PROJECT CODE AND NAME: 4902 - DISTRICT DEVELOPMENT PROJECT
SUB-VOTE CODE AND NAME: 5027 - COMM DEVT, GENDER & CHILDREN
OBJECTIVE CODE AND NAME: C - IMPROVE ACCESS,QUALITY AND EQUITABLE SOCIAL SERVICES DELIVERY
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
F01C |  |  | √ | Women and Youth economic groups with loans increased from 500 to 800 by June 2019. | Loans provided to women and youth groups and supervision done | 28 | √ |  |  | 226127400 | 62740000 | 27.7454 | Women and youth groups to be facilitated according to revenue collection
PROJECT CODE TOTAL | [9 empty] | 226127400 | 62740000 | 27.7454
SUB-VOTE TOTAL | [9 empty] | 226127400 | 62740000
PROJECT CODE AND NAME: 4101 - ROAD SECTOR PROGRAMME SUPPORT
SUB-VOTE CODE AND NAME: 5014 - WORKS
OBJECTIVE CODE AND NAME: D-INCREASE QUANTITY AND QUALITY OF SOCIAL SERVICES AND INFRASTRUCTURE
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
D03S |  |  | √ | To carry out routine maintainence 432km, spot improvement 27km, periodic maintainance 12.5km, culvert construction 26 Nos and conducting supervision of 63 roads by June, 2019 | Work on progress | 31 | √ |  |  | 501000000 | 156204745 | 31.1786 | Work on progress
SUB-VOTE TOTAL | [9 empty] | 501000000 | 156204745 | 31.1786
PROJECT CODE AND NAME: 4902 - DISTRICT DEVELOPMENT PROJECT
SUB-VOTE CODE AND NAME: 5033 - AGRICULTURE
OBJECTIVE CODE AND NAME: H - MANAGEMENT OF NATURAL RESOURCES AND ENVIRONMENT IMPROVED
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYP | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Unknown | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
H02D |  |  | √ | Utilization of improved seeds increased from 6000 to 25000 kgs by June, 2019 | improved seeds provided to farmers | 17 | √ |  |  | 89000000 | 1080000 | 1.2135 | Work on progress
H03D |  |  | √ | Irrigated area increased from 450 Ha at present to 700 Ha by June, 2019 | Not conducted | 0 | √ |  |  | 12958600 | 0 | 0 | Fund not received
PROJECT CODE TOTAL | [9 empty] | 101958600 | 1080000 | 1.2135
PROJECT CODE AND NAME: 6277-LOCAL GOVT SUPPORT PROGRAMME
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
H01D |  |  | √ | Cassava production increased from 3 to5 tonnes by June 2019 | Not implemented | 0 | √ |  |  | 8867200 | 0 | 0 | Fund not released
H04D |  |  | √ | Extension services delivery to 28,000 HH improved by June 2019 | Not implemented | 0 | √ |  |  | 2600000 | 0 | 0 | Fund not released
PROJECT CODE TOTAL | [9 empty] | 11467200 | 0 | 0
SUB-VOTE TOTAL | [9 empty] | 113425800 | 1080000 | 1.2135
PROJECT CODE AND NAME: 4902 - DISTRICT DEVELOPMENT PROJECT
SUB-VOTE CODE AND NAME: 5034 -LIVESTOCK
OBJECTIVE CODE AND NAME: H-MANAGEMENT OF NATURAL RESOURCES AND ENVIRONMENT IMPROVED
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
H01D |  |  | √ | Local chickens per HH increased from 15 to 28 by June 2019 | Not implemented | 0 | √ |  |  | 9000000 | 0 | 0 | Fund not released
H02D |  |  | √ | Milk yield production of dairy cattle/goats increased from 4 to 10 litres and 1 to 1.5 litres per cow/goat per day by June 2019 | Not implemented | 0 | √ |  |  | 49300000 | 0 | 0 | Fund not released
H05D |  |  | √ | Established slaughter slab from 0 at present to 1 by June 2019 | Not implemented | 0 | √ |  |  | 10000000 | 0 | 0 | Fund not released
H01S |  |  |  | Fish production increased from 400 to 1200 tonnes by June 2019 | Not implemented | 0 | √ |  |  | 60000000 | 0 | 0 | Fund not released
PROJECT CODE TOTAL | [9 empty] | 128300000 | 0 | 0
PROJECT CODE AND NAME: 6277-LOCAL GOVT SUPPORT PROGRAMME
CODES AND LINKAGES |  |  |  | ANNUAL PHYSICAL TARGET | CUMULATIVE STATUS ON MEETING THE PHYSICAL TARGET |  |  |  |  | EXPENDITURE STATUS |  |  | REMARKS ON IMPLEMENTATION
Target Code | FYDP II | P | R | Target Description | Actual Progress | Estimated % Completed | On track | At Risk | Off Track | Cumulative Budget | Cumulative Actual Expenditure | % Spent
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
H03D |  |  | √ | Fish production increased from 400 to 600 tonnes by June 2019 | Not implemented | 0 | √ |  |  | 8390000 | 0 | 0 | Fund not released
H04D |  |  | √ | Livestock and fishery extension services delivery improved from 19,000 to 22,000 HH by June 2019 | sustainable fisheries awareness, diseases | 0 | √ |  |  | 10682200 | 0 | 0 | Fund not released
[10 empty] | 19072200 | 0 | 0
SUB-VOTE TOTAL | [9 empty] | 147372200 | 0 | 0

## Sheet1
101514089.36
11100000
112614089.36 | 35000000 | 352467000
| 8900000 | 352836000
| 5000000 | 353740500
| 48900000 | 327927500
331141500
328480020